## Capstone Tracker
BEYOND LAST-CLICK — Capstone Project Tracker
Soheila Zamani ¦ SPICED Academy Berlin ¦ Graduation: April 28, 2026
PHASE | TASK | SUBTASK | STATUS | DEADLINE | PRIORITY | NOTES
PHASE 1 ¦ Business Question
| Define business question | State the core question clearly | DONE | Mar 30 | HIGH | Which channel drives conversions & how does credit change by attribution model?
| Define success metrics | What answer changes a budget decision? | DONE | Mar 30 | HIGH | Attribution model comparison showing influencer is undervalued by last-click
| Document data requirements | List what data is needed to answer the question | DONE | Mar 30 | MED | Orders, sessions, campaign spend, touchpoints — covered by 3 datasets
PHASE 2 ¦ Data Collection
| YouTube API data | Collect real channels via API (7,281 channels) | DONE | Apr 4 | HIGH | 7,281 real channels · 9 niches · 82 countries · nano/micro/macro/mega tiers
| YouTube API data | Secure API key in .env file (not hardcoded) | DONE | Apr 4 | HIGH | 3 keys in .env — protected by .gitignore
| A/B Testing dataset | Validate 588,101 rows from Kaggle | DONE | Apr 4 | HIGH | Real Facebook experiment · paid 2.55% vs organic 1.79% · H4 confirmed ✅
| Ad Performance dataset | Audit ad_events + ads + users (Dataset 3) | DONE | Apr 4 | HIGH | 400k events · 2,031 purchases · realistic 0.5% conversion · joinable via IDs
| Clean dataset folder | Remove synthetic/unused files | DONE | Apr 5 | MED | Deleted 8 unused folders/files — 3 real datasets remain
PHASE 3 ¦ Cleaning + SQL ¦ (SH#2 Tuesday)
| Notebook 02 — Cleaning | Check nulls, duplicates, dtypes on all 3 datasets | TO DO | Apr 6 | HIGH | YouTube already clean · focus on ad_events & standardizing columns
| Notebook 02 — Cleaning | Standardize channel/category names to lowercase | TO DO | Apr 6 | HIGH | Consistent naming needed before SQL loading
| Notebook 02 — Cleaning | Convert date columns to datetime format | TO DO | Apr 6 | HIGH | Timestamp column in ad_events needs parsing
| Notebook 02 — Cleaning | Remove outliers where relevant | TO DO | Apr 6 | MED | Check ad_events for unrealistic spend/impression values
| Notebook 02 — SQL | Create SQLite database (capstone.db) | TO DO | Apr 7 | HIGH | SPICED requirement — data must be stored in SQL
| Notebook 02 — SQL | Load YouTube table into SQL | TO DO | Apr 7 | HIGH | Table: youtube_influencers
| Notebook 02 — SQL | Load A/B Testing table into SQL | TO DO | Apr 7 | HIGH | Table: ab_testing
| Notebook 02 — SQL | Load ad_events + ads + users into SQL | TO DO | Apr 7 | HIGH | Tables: ad_events, ads, users — joinable via ad_id / user_id
| Notebook 02 — SQL | Write JOIN query connecting datasets | TO DO | Apr 7 | HIGH | SPICED requirement — must demonstrate SQL JOIN across tables
| Notebook 02 — SQL | Write 2–3 analytical SQL queries | TO DO | Apr 7 | MED | e.g. purchase rate by platform, conversion by ad type
PHASE 4 ¦ EDA + Stats ¦ (SH#2 Tuesday)
| H1 — Statistical test | Kruskal-Wallis: micro vs mega engagement rate | TO DO | Apr 7 | HIGH | view_per_subscriber by tier — expected: micro > mega
| H2 — Statistical test | Kruskal-Wallis: beauty/fashion vs fitness/lifestyle engagement | TO DO | Apr 7 | HIGH | view_per_subscriber by niche — post-hoc pairwise if significant
| H3 — Correlation analysis | Pearson: subscribers vs view_per_subscriber | TO DO | Apr 7 | HIGH | Expected negative correlation — larger channels less efficient
| H4 — Already confirmed ✅ | Chi-square: paid 2.55% vs organic 1.79% | DONE | Apr 4 | HIGH | p ≈ 0.000 · statistically significant · paid converts 43% better
| EDA — Dataset 3 | Purchase rate by ad platform (Facebook/Instagram etc.) | TO DO | Apr 8 | MED | Which platform drives most actual purchases?
| EDA — Dataset 3 | Conversion rate by ad type (Video/Story/Display) | TO DO | Apr 8 | MED | Which format works best?
| Merna's method rule | Compare percentages not raw numbers across datasets | TO DO | Apr 7 | HIGH | YouTube = engagement %, A/B = conversion % — do not mix raw numbers
PHASE 5 ¦ Attribution Modeling ¦ (Week 11)
| Build journey table | Customer journey: all touchpoints ordered by timestamp | TO DO | Apr 13 | HIGH | Use ad_events dataset — group by user_id, sort by timestamp
| Last-click model | 100% credit to final touchpoint before purchase | TO DO | Apr 14 | HIGH | Baseline model — what most businesses use today
| First-click model | 100% credit to first touchpoint | TO DO | Apr 14 | HIGH | Shows which channel INTRODUCES customers
| Linear model | Equal credit split across all touchpoints | TO DO | Apr 15 | HIGH | Fair equal distribution
| Time-decay model | More credit to touchpoints closer to purchase | TO DO | Apr 15 | HIGH | Weights: 1, 2, 4, 8... scaled by recency
| Comparison table | Channel × model → revenue credited matrix | TO DO | Apr 16 | HIGH | Core output of the project — shows how credit shifts by model
| Grouped bar chart | Attribution credit by channel for all 4 models | TO DO | Apr 16 | HIGH | Main visual for the presentation
PHASE 6 ¦ Visuals + Tableau ¦ (Week 11)
| Chart 1 | Grouped bar: revenue credit by channel × attribution model | TO DO | Apr 16 | HIGH | Takeaway: Influencer gets Xx more credit under time-decay vs last-click
| Chart 2 | Conversion funnel: sessions → purchase per channel | TO DO | Apr 17 | HIGH | Shows where each channel drops off
| Chart 3 | ROAS comparison: return on ad spend by channel | TO DO | Apr 17 | MED | Which channel gives best return per euro spent
| Chart 4 | Heatmap: channel × metric performance overview | TO DO | Apr 17 | MED | Quick visual summary of all channels
| Tableau dashboard | Interactive version of charts 1–4 | TO DO | Apr 18 | HIGH | Required by SPICED — export screenshots for slides too
| Chart rule | Every chart has a one-line takeaway written below it | TO DO | Apr 18 | HIGH | e.g. 'Influencer gets 3x more credit under time-decay than last-click'
PHASE 7 ¦ Presentation ¦ (Week 12)
| Slide 1 — Hook | One striking fact that proves last-click is wrong | TO DO | Apr 20 | HIGH | e.g. 'Brands using last-click miss 60% of influencer value'
| Slide 2 — Problem | What does a brand lose by using last-click? | TO DO | Apr 20 | HIGH | Business impact — budget wasted on wrong channels
| Slide 3 — Methodology | Data + method — simple, no jargon | TO DO | Apr 21 | HIGH | 3 datasets · 4 models · transparent about organic proxy
| Slides 4–6 — Findings | 3 findings, one per slide, chart + one-line takeaway | TO DO | Apr 22 | HIGH | H1 result, H4 result, attribution comparison
| Slide 7 — Recommendation | Which model should e-commerce brands use and why? | TO DO | Apr 23 | HIGH | Time-decay or linear — justified with data
| Slide 8 — Next steps | Concrete actions + 90-day measurement plan | TO DO | Apr 23 | MED | What a brand should do starting Monday
| GitHub cleanup | README updated with final dataset counts + run instructions | TO DO | Apr 24 | HIGH | Must be clean and professional for portfolio
| GitHub cleanup | All notebooks named correctly and run top-to-bottom | TO DO | Apr 24 | HIGH | 01_ 02_ 03_ 04_ 05_ naming convention
| Rehearsal | Practice full 10–15 minute presentation 3 times | TO DO | Apr 25 | HIGH | Time yourself — 10 min content + 5 min Q&A
| Final check | All SPICED requirements confirmed | TO DO | Apr 27 | HIGH | SQL ✓ · 2-4 datasets ✓ · GitHub ✓ · Jupyter ✓ · Tableau ✓ · slides ✓
LEGEND: | DONE | IN PROGRESS | TO DO